## Project Timeline
MyBusz Research Proj
TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | DURATION in weeks | COMMENTS
Learn React & Make UI Frame | In Progress | Aeron, Qi Rong | 2020-06-22 | 2020-07-03 | 11 | 1.5714
Learn Flask + do up UI in flask + Apply Google for data cleanup completion | In Progress | Hui Jie | 2020-06-22 | 2020-07-06 | 14 | 2
Connect DB, App backend functions, fetch data | Not Started | Aeron, Qi Rong | 2020-07-06 | 2020-07-22 | 16 | 2.2857
Connect DB, Web backend functions, fetch data | Not Started | Hui Jie | 2020-07-06 | 2020-07-22 | 16 | 2.2857
Testing & Review | Not Started | Aeron, Qi Rong, Hui Jie | 2020-07-22 | 2020-07-30 | 8 | 1.1429
Changes | Not Started | Aeron, Qi Rong, Hui Jie | 2020-08-03 | 2020-08-07 | 4 | 0.57143
Final Review and Changes | Not Started | Aeron, Qi Rong, Hui Jie | 2020-08-10 | 2020-08-24 | 14 | 2 | Rough number
Future Implementations | Not Started | Aeron, Qi Rong, Hui Jie | 2020-08-24 | 2020-09-24 | 31 | 4.4286 | Rough number